## Sheet1
LOG BOOK
|  |  | Project Name | Mental Health ChatBot using RAG | PRN | 21070122027 |  | PASS | Partial | Fail
|  |  | Purpose | B.Tech Final Project | Year | Final Year |  | 7 | 1 | 11
|  |  | Name | Aryan Sharma | Batch | 2021 - 25
SR No | Date | Time | File | Changes | Time Taken | Remarks | Reason
1 | 2024-04-16 | 13:52 | ADDED | Collected all the PDFs, JSON and CSV files from their sources. PDFs were taken from Mind.co.uk website | 3 Days | Partially Successful
2 | 2024-06-29 | 12:36 | ADDED | Collected all the PDFs, JSON and CSV files from their sources. PDFs were taken from Mind.co.uk website | 1 Day | Successful
3 | 2024-07-19 | 12:17 | EXECUTION | Created and executed python script to convert PDF, JSON and CSV Files to respective text files | 1.5 Hour | Failed | Module Error
4 | 2024-07-19 | 13:41 | EXECUTION | Created and executed python script to convert PDF, JSON and CSV Files to respective text files | 0.5 Hour | Failed | Module Error
5 | 2024-07-19 | 14:22 | EXECUTION | Created and executed python script to convert PDF, JSON and CSV Files to respective text files | 1.5 Hour | Failed | Wrong Output
6 | 2024-07-19 | 15:50 | EXECUTION | Created and executed python script to convert PDF, JSON and CSV Files to respective text files | 3 Min | Successful
7 | 2024-07-19 | 15:54 | ADDED | Processed folder with a sub folder Text created and all text files were stored | NA | Successful
8 | 2024-07-19 | 17:30 | ADDED | Added more dataset CSV files | 5 Min | Successful
9 | 2024-07-19 | 17:40 | ADDED | New text files added for the new dataset files | 5 Min | Successful
10 | 2024-07-21 | 13:00 | EXECUTION | Created and executed python script to preprocess the text files and store them in another folder called processed | 1 HOUR | Failed | Module Error
11 | 2024-07-21 | 14:00 | EXECUTION | Created and executed python script to preprocess the text files and store them in another folder called processed | 15 Mins | Failed | Download Error
12 | 2024-07-21 | 14:15 | EXECUTION | Created and executed python script to preprocess the text files and store them in another folder called processed | 32 Mins | Failed | Infinity Loop
13 | 2024-07-22 | 14:47 | EXECUTION | Created and executed python script to preprocess the text files and store them in another folder called processed | 2 HOURS | Successful
14 | 2024-07-22 | 16:47 | ADDED | Preprocessed Text files stored in data/processed/preprocessed | NA | Successful
10 | 2024-07-28 | 22:00 | EXECUTION | Created and executed python script to get documents(PDF only for now), create a document object, breaking it into chunks(chunking) | 1 HOUR | Failed | Module Error
11 | 2024-07-28 | 23:00 | EXECUTION | Created and executed python script to get documents(PDF only for now), create a document object, breaking it into chunks(chunking) | 1 HOUR | Failed | Module Error
12 | 2024-07-29 | 24:00 | EXECUTION | Created and executed python script to get documents(PDF only for now), create a document object, breaking it into chunks(chunking) | 1 HOUR | Failed | Module Error
13 | 2024-07-29 | 25:00 | EXECUTION | Created and executed python script to get documents(PDF only for now), create a document object, breaking it into chunks(chunking) | 1 HOUR | Failed | Module Error
14 | 2024-07-29 | 26:00 | EXECUTION | Created and executed python script to get documents(PDF only for now), create a document object, breaking it into chunks(chunking) | 1 HOUR | Failed | Module Error
15 | 2024-07-29 | 27:00 | EXECUTION | Created and executed python script to get documents(PDF only for now), create a document object, breaking it into chunks(chunking) | 45 mins | Successful
16 | 2024-07-29 | 8:45 | EXECUTION | Created and executed files for creating vectors and storing it in Chroma DB | 3 HOURS | Failed | Module Error